## Planned Test Cases
Receiving and Assignment | Activities planned for MARCH 3rd thru March 7th 1 - The Following Activities are planned for Monday March 3rd. Plan to send about 150 Vins From GALC to .NET and ProAct. Repeat sending 150 Vins for the next 5 days. 2 - Vin List should contain 100KA Vins, 30 KC Vins and 20 Export Vins. Need to make sure we have orders in the system 3 - No Monroney or parking ticket printing 4 - Check for any Zone assignments and Holds, Check for Allocation Warehouse code 5 - If any vehicle has Zones Hold ensure to validate
Create AFOFF(40A) transactions for Several Vins
Place VQ Ship (50A) transactions in Queue
Create AH-RCVD 60A transaction and Place in Queue for GALC
Retrieve AH-RCVD (60A) from Queue and Process
Process VQship (50A ) and assign parking location for dealer assigned Vins. Place Un-assigned units in FTZ
Create PARK CHANGE (65A) with the ZPL data
Transmit PARK CHANGE (65A) in Queue
Process PARK CHANGE (65A)
Print Monroney label on the label printer
Print Parking ticket label
Process PARK CHANGE (65A)
Un Assignment | Activities planned for MARCH 3rd thru March 7th 1 - Perform un-Assignment for 10 Vins 2 - Validate ASN Files 3 - .NET team to validate the Vin Activities
Initiate Un-Assignment for several Vins in ProAct system
Initiate parking move to FTZ and send transaction to Net
Communicate with Truck carriers and remove VIN from ASN
Process Un-Assignment
Change status to 'G' (Receiving Status) and update Parking Location
Parking Move | Activities planned for MARCH 3rd - MARCH 7th 1 - Perform un-Assignment for 10 Vins 2 - Validate ASN Files
Initiate a parking change for several Vins in ProAct system
Send ASN to Truck Carriers with new Location
Create PARK CHANGE (65A) transition in ProAct and transmit to .NET
Verify in MQ_Transaction_Log table for 65A transaction details sent to GALC
Process PARK CHANGE (65A)
Truck Shipping
Process Truck car Shipping | Activities planned for MARCH 3rd - March 7th 1 - perform Truck shipping for 15 Units 2 - Validate AH_SHIP sent to GALC 3 - Validate Vin Activity sent to Host Mainframe 4 - Process all records in Host
Truck Unshipping | Activities planned for MARCH 3rd - March 7th 1 - Process Truck un-shipment for 3 units 2 - Validate Vehicle Returned and parking location updated Validate .NET and Mainframe activities
Process Truck Unshipping
Proact initiate Truck Un shipment and send request to YMS
YMS process Truck unshipping
Load to Train | Activities planned for MARCH 4th - March 7th 1 - Load to Train for 15 KA Units 2 - Load to Train for 5 KC units 3 - Validate Vin Activity 4 - Ensure ON-TRN has been sent GALC 5 - Check Rail Spot Sheet
Proact process Load to Train
Create 75A(AH-SHIP) and send to YMS
Process 75A(AH-SHIP) transaction
YMS Process Truck Shipping and send load Make up to Host VIN5 HI1/IJ1
YMS send ON-TRN in transaction 70A(DLR-ASGN and 75A(AH-SHIP) to factory
Check Rail Spot Sheet
Rail Shipping | Activities planned for MARCH 4th - March 7th 1 - Perform Rail shipment for 15 KA Units from previous activity 2 - Perform Rail shipment for 5 KC units from previous activity 3 - Validate Vin Activity 4 - Check Commercial invoice
Process Rail car shipping and scan vehicle on ASN
Display "GO" or "STOP"
if "GO" Place the unit on Rail Car
Send 75A(AH-SHIP) to YMS
Process 75A(AH-SHIP) transaction & Rail car shipping
Commercial invoice/Rail Bill of Lading | Activities planned for MARCH 4th - March 7th 1 - Execute Commerical invoice, Rail bill of Lading from the Host 2 - Validate report printed. 3 - Request re-print of the report from ProAct APP the next day
Generate Commercial Invoice from .NET
Request Re-print from ProAct
Return to Plant | Activities planned for MARCH 3rd 1 - Perform Return to plant for 5 units Rail and Truck assigned units 2 - Validate AH_RTN sent to GALC 3 - Validate Parking Location change 4 - Validate ASN file sent to trucking company
Initiate Return to Plant for several Vins in ProAct system
All parking assignments of the vehicle is removed
All the vehicle holds are removed except for the PPO vehicle
Send Updated ASN to Trucking company
Receive 90A (AH-RTN)
YMS send update to Proact system
Re-Receive the unit after Return to plant | Activities planned for MARCH 4th 1 - Re-receive Units Returned to plant 2 - Validate new Assignment and all the transactions 3 - Validate Parking location
Rail Unshipping | Activities planned for MARCH 4th 1 - Perform Rail - Unship for 2 units that were shipped previous rail ship activity 2 - Check Vehicle status 3 - Validate Parking location
Process Rail car Unshipping and scan vehicles on Rail car
YMS process Rail car unshipping
Place and Remove Hold codes/Stop Ship | Activities planned for MARCH 3rd - March 7 1 - Place Hold on Units and Remove 2 - Validate ASN files 3 - Validate Vin Activity file
Select Few Vins and Place hold codes in ProAct system
Warehouse Transfer From ProAct to AS400 | Activities planned for MARCH 5 - March 6 1 - Perform Warehouse transfer for few units 2 - Validate unit assigned to correct Warehouse dealer 3 - Validate Vin Activity sent to Host 4 - Host to run the jobs and create In-Transit file
Initiate Warehouse transfer for several Vins in ProAct system, Select Un-assigned vins
BodySHop Transfer From ProAct to AS400 | Activities planned for MARCH 5 - March 6 1 - Perform BodyShop transfer for few units - Validate unit assigned to correct Bodyshop dealer 3 - Vlaidate Vin Activity sent to Host 4 - Host to run the jobs and create In-Transit file
Initiate Warehouse transfer for several vins in ProAct system, Select Un-asigned vins
Shuttle units from MAP to ELP and Carrier/Destination changes | Activities planned for MARCH 6 - March 7 1 - Perform SHuttle transfer - Perform Carrier/ Destination changes for several units and ship confirm 3 - Validate vin activity in ProAct, .Net and Host
Perform Shuttle transfer from MAP to ELP Perform Carrier/Destination changes
YMS Report validate | Activities planned for MARCH 4th - March 7 1 - Validate YMS reports
Pre-Receiving Hold | Activities planned for MARCH 5 - March 6 1 - Select amodel and few dealer and set in Pre-receiving hold 2 - Send VQ_SHIP transaction that matches these units and validate that a hold is placed on them 3 - Test Different scenario's
QIP Process
QIP Process on Mobile app QIP Process on ProAct Web Version | Activities planned for MARCH 6th- March 7th 1 - perform QIP for 5 units on Mobile APP 2 - Perform QIP on 5 units on ProAct App Web version
Parking Group Maintenance
Set up and Remove specific parking location Assign specific models to new parking location | Activities planned for MARCH 6th- March 7th 1 - Set up and Remove specific parking location 2 - Assign specific models to new parking location

## UAT Test Script
2024-09-23
Task | Date From To |  | Revised Startdate End Date | Dept in charge |  |  |  |  | Pass to(comments) (See contact list)
Preparation Activity (test Data and Environment) |  |  |  | Responsible Group |  | Completion Date | Delay in Days | SIT Execution Status | Comments
UAT Planning Kick off meeting |  |  |  | All Teams
Identify test data that needs to be sent to .Net from Host |  |  |  | All Teams
Ensure test Queue are set up and active |  |  |  | All Teams
Create Orders needed for testing |  |  |  | Auto ISD
Confirm If we need Test Jobs to send files to .Net are ready |  |  |  | Mainframe Team
Select orders that will Match the MTOC that will be send by GALC |  |  |  | Mainframe Team
Confirm UAT Data bases are ready |  |  |  | All Teams
Create 40A and 50A transactions for the Vins to be sent to .Net |  |  |  | GALC Team | VSC Tem
Identify Label and Parking test printers for testing and provide information to all teams |  |  |  | Auto ISD
Batch Jobs
Verify Mainframe to YMS Interface Job runs at everyday night |  |  |  | .Net Team
While running the Interface Job sub job (For Example: ELO230C) runs |  |  |  | .Net Team
Interface files contains the Master table information |  |  |  | .Net Team
Host Mainframe will place the Interface file (For Example: INT304CLY(NA) in FTP location |  |  |  | Mainframe Team
ELO230C job will read the interface file : INT304CLY(NA) from FTP location |  |  |  | .Net Team
job will save the data from interface files data into Out Files : ODC305EF |  |  |  | .Net Team
Go to the OutFile : ODC305EF check for the File description : ALSIS: Canada Language Code by Dealer E/F and Mode : Input |  |  |  | .Net Team
For the YMS db name in DB Design sheet and take the YMS db table name |  |  |  | .Net Team
Verify if the updation is happening in new YMS db table :dbo.Dealer for ODC305EF |  |  |  | .Net Team
Verify In dbo.Dealer table in YMS db if all the fields got updated after running the job : ELO230C |  |  |  | .Net Team
Transmit Master files and order file to .Net and ProAct System
Dealer Data : INT304 |  |  |  | .Net Team | VSC Tem
Master Data : INT305 |  |  |  | .Net Team | VSC Tem
Master Data : INT305(Cont) |  |  |  | .Net Team | VSC Tem
Model Data : INT307 |  |  |  | .Net Team | VSC Tem
PFIFPPOData : INT310FTP |  |  |  | .Net Team | VSC Tem
Intransit (inbound) : INT919 |  |  |  | .Net Team | VSC Tem
Dealer Order Header : INT928 |  |  |  | .Net Team | VSC Tem
Dealer Order Detail : INT930 |  |  |  | .Net Team | VSC Tem
Dealer Order Header (reinsert RTP order): INT928FTP |  |  |  | .Net Team | VSC Tem
Dealer Order Detail (reinsert RTP order):INT930FTP |  |  |  | .Net Team | VSC Tem
INT940 |  |  |  | .Net Team | VSC Tem
CH Exterior Color - INTFL2P |  |  |  | .Net Team | VSC Tem
CH Interior Color - INTFL3P |  |  |  | .Net Team | VSC Tem
CH Model Feature - INTFL4P |  |  |  | .Net Team | VSC Tem
CH Model Color - INTFL6P |  |  |  | .Net Team | VSC Tem
CH Umodel - INTFL7P |  |  |  | .Net Team | VSC Tem
Transmit Dealer Master, Dealer Routes, Model Master, Color Master and all files required for testing |  |  |  | Mainframe Team
Transmit Order Stack file |  |  |  | Mainframe Team
Validate the files have been received and uploaded to Tables |  |  |  | .Net Team | VSC Tem
Transmit Files to ProACt system |  |  |  | .Net Team | VSC Tem
Validate the files have been received and uploaded to Tables |  |  |  | ProACT
Receiving and Assignement
Create AFOFF(40A) transactions for Several Vins | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Place AFOFF(40A) transaction in Queue for YMS | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Verify in MQ_Transaction_Log table for 40A transaction details sent to YMS | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Retreive AFOFF(40A) transaction and Process | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Validate the AF OFF has been inserted in Correct tables | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Create AFOFF(40A) transactions for ProAct and transmit | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Reterive AFOFF(40A) transaction and build vehicle record in ProAct system | 2025-03-03 | 2025-03-21 |  | ProACT
Create VQ ship (50A) Transaction that will match MTOC's in the order file | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Create VQ ship (50A) Transaction that will not match MTOC's in the order file | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Place VQ Ship (50A) transactions in Queue | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Verify in MQ_Transaction_Log table for 50A transaction details sent to YMS | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Create AH-RCVD 60A transaction and Place in Queue for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Process VQship (50A ) in .Net system by receiving and assigning to the dealer orders. The Vins that do not match the dealer order should be un-assigned. | 2025-03-03 | 2025-03-21 |  | .Net Team
Reterive AH-RCVD (60A) from Queue and Process | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Transmit VQ Ship (50A) Messages in Queue for ProACT | 2025-03-03 | 2025-03-21 |  | .Net Team
Process VQship (50A ) and assign parking location for dealer assigned Vins. Place Un-assigned units in FTZ | 2025-03-03 | 2025-03-21 |  | ProACT
Create PARK CHANGE (65A) with the ZPL data | 2025-03-03 | 2025-03-21 |  | ProACT
Transmit PARK CHANGE (65A) in Queue | 2025-03-03 | 2025-03-21 |  | ProACT
Process PARK CHANGE (65A) | 2025-03-03 | 2025-03-21 |  | .Net Team
Print Monroney label on the label printer | 2025-03-10 | 2025-03-21 |  | .Net Team
Print Parking ticket label | 2025-03-10 | 2025-03-21 |  | .Net Team
Create PARK CHANGE (65A) transaction for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Place PARK CHANGE (65A) transaction in Queue for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Verify in MQ_Transaction_Log table for 65A transaction details sent to GALC | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Process PARK CHANGE (65A) | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Create transactions for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue to Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Mainframe receives and process the message | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Mainframe saves the data in its Database | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for transaction details sent to Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Un-Assignment | 2025-03-03
Initiate Un-Assignment for several vins in ProAct system | 2025-03-03 | 2025-03-21 |  | ProACT
Initiate parking move to FTZ and send transaction to Net | 2025-03-03 | 2025-03-21 |  | ProACT
Verify in dbo.APITransactions table for details of transcation from Proact | 2025-03-03 | 2025-03-21 |  | .Net Team
Communicate with Truck carriers and remove VIN from ASN | 2025-03-03 | 2025-03-21 |  | ProACT
Process Un-Assignment | 2025-03-03 | 2025-03-21 |  | .Net Team
Change status to 'G' (Receiving Status) anad update Parking Location | 2025-03-03 | 2025-03-21 |  | .Net Team
Verify in VIN_Detail table for status update and parking location | 2025-03-03 | 2025-03-21 |  | .Net Team
YMS send VIN activity to Host Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Verify in yms.dbo.VIN_Activity table for host transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
VIN is PPO, and VIN not checked, remove PPO details and Send GG4/HH4 delete to host | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue to Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for GG9/HH9 transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
If VIN is Zone hold, Send GG6 to Host | 2025-03-03 | 2025-03-21 |  | .Net Team
PPO VIN then remove hold code 57 and send HH8 to Host | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue to Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for HH8 transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
Process transaction | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Parking Move
Initiate a parking change for several vins in ProAct system | 2025-03-03 | 2025-03-21 |  | ProACT
Send ASN to Truck Carriers with new Location | 2025-03-03 | 2025-03-21 |  | ProACT
Create PARK CHANGE (65A) transition in ProAct and transmit to .Net | 2025-03-03 | 2025-03-21 |  | ProACT
Verify in APITransactions table in YMS for 65A details | 2025-03-03 | 2025-03-21 |  | .Net Team
Process PARK CHANGE (65A) transaction | 2025-03-03 | 2025-03-21 |  | .Net Team
Create PARK CHANGE (65A) transaction for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Place PARK CHANGE (65A) transaction in Queue for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Verify in MQ_Transaction_Log table for 65A transaction details sent to GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Process PARK CHANGE (65A) | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
Create transactions VIN5 GG9/HH9 for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue to Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for GG9/HH9 transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
Load to Train
Proact process Load to Train | 2025-03-04 | 2025-03-21 |  | ProACT
Fields Rail_car_id and Seals to get the rail details from ProAct | 2025-03-04 | 2025-03-21 |  | ProACT
All rail relationship will be inserted in Rail Load before Rail shipping | 2025-03-04 | 2025-03-21 |  | ProACT
Remove all parking assignments | 2025-03-04 | 2025-03-21 |  | .Net Team
Create 75A(AH-SHIP) and send to YMS | 2025-03-04 | 2025-03-21 |  | .Net Team
Verify in APITransactions table for 75A transaction details sent to YMS | 2025-03-04 | 2025-03-21 |  | .Net Team
Process 75A(AH-SHIP) transaction | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS Process Truck Shipping and send load Make up to Host VIN5 HI1/IJ1 | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Place in queue for Mainframe | 2025-03-04 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-04 | 2025-03-21 |  | .Net Team
Check in yms.dbo.VIN_Activity table for Vin5 HI1/IJ1 transaction details | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS send ON-TRN in transaction 70A(DLR-ASGN and 75A(AH-SHIP) to factory | 2025-03-04 | 2025-03-21 |  | .Net Team
Place 70A(DLR-ASGN) and 75A(AH-SHIP) transactions in Queue for GALC | 2025-03-04 | 2025-03-21 |  | .Net Team
Verify in MQ_Transaction_Log table for 70A&75A transaction details sent to GALC | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS send in-transit to Host | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS Process Truck Shipping and send load Make up to Host VIN5 HI1/IJ1 | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Place in queue for Mainframe | 2025-03-04 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 HI1/IJ1 transaction details | 2025-03-04 | 2025-03-21 |  | .Net Team
Rail Shipping
Process Rail car shipping and scan vehicle on ASN | 2025-03-04 | 2025-03-21 |  | ProACT
Display "GO" or "STOP" | 2025-03-04 | 2025-03-21 |  | ProACT
iF "GO" Place the unit on Rail Car | 2025-03-04 | 2025-03-21 |  | ProACT
Process Shipment Confirmation and Rail load message to .Net | 2025-03-04 | 2025-03-21 |  | ProACT
Send 75A(AH-SHIP) to YMS | 2025-03-04 | 2025-03-21 |  | ProACT
Verify in APITransactions table for 75A transaction details sent to YMS | 2025-03-04 | 2025-03-21 |  | .Net Team
Process 75A(AH-SHIP) transaction & Rail car shipping | 2025-03-04 | 2025-03-21 |  | .Net Team
Create 70A(DLR-ASGN) and 75A(AH-SHIP) for GALC | 2025-03-04 | 2025-03-21 |  | .Net Team
Place 70A(DLR-ASGN) and 75A(AH-SHIP) transactions in Queue for GALC | 2025-03-04 | 2025-03-21 |  | .Net Team
Verify in MQ_Transaction_Log table for 70A&75A transaction details sent to GALC | 2025-03-04 | 2025-03-21 |  | .Net Team
Send the in Load make up and shipping Vin5 HI1/IJ1 to Host | 2025-03-04 | 2025-03-21 |  | .Net Team
Place in queue for Mainframe | 2025-03-04 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 HI1/IJ1 transaction details | 2025-03-04 | 2025-03-21 |  | .Net Team
Process Rail shipment in Host | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Truck Shipping
Proact process Truck Shipping | 2025-03-03 | 2025-03-21 |  | ProACT
Remove all parking assignments | 2025-03-03 | 2025-03-21 |  | ProACT
Create 75A(AH-SHIP) and send to YMS | 2025-03-03 | 2025-03-21 |  | ProACT
Verify in APITransactions table for 75A transaction details sent to YMS | 2025-03-03 | 2025-03-21 |  | .Net Team
Process 75A(AH-SHIP) transaction | 2025-03-03 | 2025-03-21 |  | .Net Team
YMS Process Truck Shipping and send load Make up to Host VIN5 HI1/IJ1 | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 HI1/IJ1 transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
YMS send 70A(DLR-ASGN and 75A(AH-SHIP) to factory | 2025-03-03 | 2025-03-21 |  | .Net Team
Place 70A(DLR-ASGN) and 75A(AH-SHIP) transactions in Queue for GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
Verify in MQ_Transaction_Log table for 70A&75A transaction details sent to GALC | 2025-03-03 | 2025-03-21 |  | .Net Team
YMS send in-transit to Host | 2025-03-03 | 2025-03-21 |  | .Net Team
YMS Process Truck Shipping and send load Make up to Host VIN5 HI1/IJ1 | 2025-03-03 | 2025-03-21 |  | .Net Team
Place in queue for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 HI1/IJ1 transaction details | 2025-03-03 | 2025-03-21 |  | .Net Team
Return to Plant
Initiate Return to Plant for several vins in ProAct system | 2025-03-03 | 2025-03-21 |  | ProACT
All parking assignments of the vehicle is removed | 2025-03-03 | 2025-03-21 |  | ProACT
All the vehicle holds are removed except for the PPO vehicle | 2025-03-03 | 2025-03-21 |  | ProACT
Send Updated ASN to Trucking company | 2025-03-03 | 2025-03-21 |  | ProACT
Send AH_TRN to .Net Team | 2025-03-03 | 2025-03-21 |  | ProACT
YMS send 90A(AH-RTN) transaction to GALC | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Receive 90A (AH-RTN) | 2025-03-03 | 2025-03-21 |  | GALC Team | VSC Tem
send HH4 trascn to mainframe with transn change code=D and trnscn data= Blanks | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Remove all hold for the VIN | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
YMS send VIN activity to Host Mainframe RTP VIN5 GE1 | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Receive transactions and Process | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Return order to order stack | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Send new order stack to .Net | 2025-03-03 | 2025-03-21 |  | Mainframe Team
YMS send update to Proact system | 2025-03-03 | 2025-03-21 |  | .Net Team | VSC Tem
Re-Receive the unit after Return to plant
Rail Unshipping
Process Rail car Unshipping and scan vehicles on Rail car | 2025-03-06 | 2025-03-21 |  | .Net Team
YMS process Rail car unshipping | 2025-03-06 | 2025-03-21 |  | .Net Team
YMS send unship VIN5 JI1/IH1 to Host | 2025-03-06 | 2025-03-21 |  | .Net Team
Place in queue for Mainframe | 2025-03-06 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-06 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 JI1/IH1 transaction details | 2025-03-06 | 2025-03-21 |  | .Net Team
Truck Unshipping
Process Truck Unshipping | 2025-03-04 | 2025-03-21 |  | .Net Team
Proact initiate Truck unshipment and send request to YMS | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS process Truck unshipping | 2025-03-04 | 2025-03-21 |  | .Net Team
YMS send unship VIN5 JI1/IH1 to Host | 2025-03-04 | 2025-03-21 |  | .Net Team
Place in queue for Mainframe | 2025-03-04 | 2025-03-21 |  | .Net Team
Receive Messages and process in Mainframe | 2025-03-04 | 2025-03-21 |  | Mainframe Team
Check in yms.dbo.VIN_Activity table for Vin5 JI1/IH1 transaction details | 2025-03-04 | 2025-03-21 |  | .Net Team
Place and Remove Hold codes/Stop Ship
Select Few vins and Place hold codes in ProAct system | 2025-03-03 | 2025-03-21 |  | ProACT
Create Hold Code transaction for .Net | 2025-03-03 | 2025-03-21 |  | ProACT
Create ASN delete transaction for Truck carriers and Send to carrier | 2025-03-03 | 2025-03-21 |  | ProACT
Transmit Hold code transaction to .Net | 2025-03-03 | 2025-03-21 |  | .Net Team
Process transaction | 2025-03-03 | 2025-03-21 |  | .Net Team
Create transaction for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Place transaction in Queue for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Process Hold tranascation in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Remove Hold code from the vins in Previous example | 2025-03-03 | 2025-03-21 |  | ProACT
Create transaction for .Net | 2025-03-03 | 2025-03-21 |  | ProACT
Transmit Hold code remova to .Net | 2025-03-03 | 2025-03-21 |  | ProACT
Process transaction | 2025-03-03 | 2025-03-21 |  | .Net Team
Create transaction for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Place transaction in Queue for Mainframe | 2025-03-03 | 2025-03-21 |  | .Net Team
Process Hold tranascation in Mainframe | 2025-03-03 | 2025-03-21 |  | Mainframe Team
Warehouse Transfer From ProAct to AS400
Initiate Warehouse transfer for several vins in ProAct system, Select Un-asigned vins |  |  |  | ProACT
Change dealer code to Warehouse dealer code |  |  |  | ProACT
Send ASN to ship carrier and generate ship confirmation |  |  |  | ProACT
Send transaction to .Net system |  |  |  | ProACT
Receive transaction from .Net and Process |  |  |  | .Net Team
Send Ship confirmation to Factory |  |  |  | .Net Team
Validate order stays with vehicle |  |  |  | .Net Team
Send VIN activity to Host Mainframe |  |  |  | .Net Team
Create In-transit record for Warehouse transfer |  |  |  | Mainframe Team
Send In-transit record to AS400 YMS for testing |  |  |  | Mainframe Team
Process In-transit Record |  |  |  | AS400 Team
Receive Record into System |  |  |  | AS400 Team
Proact assign Parking location for receiving yard |  |  |  | ProACT
Body Shop Transfer
Initiate Body Shop transfer for several vins in ProAct system |  |  |  | ProACT
Change dealer code to Warehouse dealer code |  |  |  | ProACT
Verify in dbo.VIN_Activity table "Transaction_Data_Text " field |  |  |  | .Net Team
All parking assignments of the vehicle is removed |  |  |  | ProACT
All the vehicle holds are removed except for the PPO vehicle |  |  |  | ProACT
Communicate with Trucking company and remove VIN from ASN |  |  |  | ProACT
Change the status to “G” from "H" |  |  |  | .Net Team
Verify in VIN_Detail table with Vin_Unit_Status_Code column |  |  |  | .Net Team
VIN is PPO and not checked In , then remove PPO detail |  |  |  | .Net Team
Verify in PPO_Vehicle_Price table for the the VIN deletion |  |  |  | .Net Team
Send Unassigned HG1 and GG7 to host mainframe |  |  |  | .Net Team
Verify in yms.dbo.VIN_Activity table for the host tarnsaction details |  |  |  | .Net Team
Send GG4 Delete to host |  |  |  | .Net Team
Once the repair is complete , Send 70A(DLR-ASGN) and 75A(AH-SHIP) to GALC |  |  |  | .Net Team
Verify in MQ_Transaction_Log table for 70A&75A transaction details sent to GALC |  |  |  | .Net Team
Send 70A(DLR-ASGN) and 75A(AH-SHIP) to ProAct |  |  |  | .Net Team
ETL
ETL job runs after configured interval of time |  |  |  | ETL Team
Within the stored procedure ETL job checks the Data_Sync table |  |  |  | ETL Team
ETL job runs for the first time then there should be no data in the Data_Sync table |  |  |  | ETL Team
DOT_NET_START_TS column gets updated with current date and time values In the Data_Sync table |  |  |  | ETL Team
Data will be loaded from YMS tables to the ETL tables |  |  |  | ETL Team
DOT_NET_END_TS column gets updated after the data is loaded to ETL tables |  |  |  | ETL Team
DOT_NET_END_TS column gets updated with current date and time values |  |  |  | ETL Team
In the FTP location worker process creates an empty file |  |  |  | ETL Team
Zena job constantly looks for the empty file in the FTP location |  |  |  | ETL Team
Once the empty file is detected by the Zena job then job will get triggered and ETL will extract the data from the tables |  |  |  | ETL Team
ETL updates the ETL_START_TS column in the Data_Sync table with the date and time when the extraction of data has started |  |  |  | ETL Team
ETL job updates the ETL_END_TS column in the Data_Sync table with the date and time when the extraction of data has completed |  |  |  | ETL Team
Verify that the empty file is deleted |  |  |  | ETL Team
After an hour .Net checks if the file exists in FTP location |  |  |  | .Net Team
In the Data_Sync table .Net checks the ETL completion time stamp |  |  |  | .Net Team
Verify If the file doesn’t exists and timestamp is updated by ETL |  |  |  | ETL Team
Then it will delete the existing records in Staging tables and it will check in Data_Sync table within stored procedure |  |  |  | ETL Team
Verify if the file exists or timestamp is not updated by ETL in Data_Sync table |  |  |  | ETL Team
Then it will send an Email to both the support teams |  |  |  | ETL Team
ETL job runs not for the first time, Then there should be data in the Data_Sync table |  |  |  | ETL Team
To check the latest value of DOT_NET_START_TS column verify Data_Sync table |  |  |  | ETL Team
ETL_END_TS column should not be null |  |  |  | ETL Team
Check whether all YMS_ETL tables are truncated |  |  |  | .Net Team
Load only the data where the condition last_update_timestamp > DOT_NET_START_TS satisfies |  |  |  | .Net Team
DOT_NET_END_TS column is updated with current date and time values ater the load is completed |  |  |  | .Net Team
In the FTP location worker process creates an empty file |  |  |  | ETL Team
Then the Zena job should be constantly looking for the empty file in the FTP location |  |  |  | ETL Team
Once the empty file is detected by the Zena job,Then job will get triggered and ETL will extract the data from the tables |  |  |  | ETL Team
ETL updates the ETL_START_TS column in the Data_Sync table with the date and time when the extraction of data has started |  |  |  | ETL Team
ETL job update the ETL_END_TS column in the Data_Sync table with the date and time when the extraction of data has completed |  |  |  | ETL Team
Verify that the empty file is deleted |  |  |  | ETL Team
After an hour .Net checks if the file exists in the FTP location |  |  |  | .Net Team
.Net checks the ETL completion time stamp on Data_Sync table |  |  |  | .Net Team
Verify If the file doesn’t exists and timestamp is updated by ETL |  |  |  | ETL Team
Then it will delete the existing records in Staging tables and within stored procedure it will check in Data_Sync table |  |  |  | ETL Team
Verify if the file exists or timestamp is not updated by ETL in Data_Sync table |  |  |  | ETL Team
Then it will send an Email to both the support teams |  |  |  | ETL Team
Proact API is responsible to fill Proact related ETL tables |  |  |  | ProACT
User provides the Proact URL in the Postman |  |  |  | .Net Team
User provides the sample request with all the mandatory and option fields in the postman |  |  |  | .Net Team
In Postman User clicks on the send button |  |  |  | .Net Team
Validate the response in JSON format with requried fields and status code as :200 OK |  |  |  | .Net Team
Verify the API fills the Proact related ETL table |  |  |  | .Net Team
Recive and Assignment (Monroney Label Print Window Sticker Print (KC) Case Mark (for Export) Built Sheet Print ) |  |  |  | .Net Team
R1-Night Batch Job |  |  |  | .Net Team
ETL Job From AHM to Mexico |  |  |  | .Net Team
Load Master Cly data |  |  |  | .Net Team
Load Model Cly data |  |  |  | .Net Team
Load In transit Cly data |  |  |  | .Net Team
Load Dealer order Cly data |  |  |  | .Net Team
End of 2E2 Cycle 2
Live activities
Confirm Business data

## Business Users Test Cases
UAT Test Case scenarios
YES/NO/QUESTION 'Q'/OTHER | ProAct response (is this available?) | Test Case # | Category | Pro Act screen | Task | Pass / Fail | Expected Result | Comment
YES | VIN management screeen | UAT1 | Operational | VIN Mgmt screen | Hold maintenance |  | Display a list of VINs on Hold currently at the DC.
Ability to maintenace VINs, individually as well as in groups.
Q | ?? Can search by next yard location and see what needs to go to FTZ. Is that what you want to see? | UAT2 | Operational | VIN Mgmt screen | Manual Dealer Assigments |  | Batch assignments from the prior night that need to be moved from FTZ.
|  | UAT3 | Screen Filtering / Sorting | VIN Mgmt screen | PPO package descriptions
Q | ?? Require more information | UAT4 | Screen Filtering / Sorting | VIN Mgmt screen | All Screen options available to test for a VIN
Q | ?? What is it they would like to view? | UAT5 | Screen Filtering / Sorting | VIN Mgmt screen | Separating Allocation Warehouse from the Hold code |  | Need to be able to sort on the WH code
NO | not available | UAT6 | Screen Filtering / Sorting | VIN Mgmt screen | Define a rule for alpha or for numeric on Hold codes |  | Ability to separate the numeric codes from the Alpha codes
NO | not available | UAT7 | Screen Filtering / Sorting | VIN Mgmt screen | View Zone holds and related WH letters |  | For unassigned units only
NO | Proact doesn't have a view of the 2nd leg | UAT8 | Screen Filtering / Sorting | VIN Mgmt screen | View of 2nd leg destination |  | Applies to Greensburg and Lincoln, Does not apply to MAP.
Inbounds from Greensburg to MAP. GOO and MOO
YES | See in Yard View screen - Rail | UAT9 | Operational | VIN Mgmt screen | Railcar loads & entering railcars
YES | Used in the case where tracksheet hasn't supplied railcar type & equipment needs to manually created | UAT10 | Operational | Equip Config | Defining railcar types
TBD | Pending - solution tbd before detail can be provided | UAT11 | Operational | Equip Config | Build spot sheets
YES | Honda VIN management search field (colour description) e.g. *red* | UAT12 | Screen Filtering / Sorting | VIN Mgmt screen | Filter by color
Q | Is this linked to UAT5? If not can we have more information? | UAT13 | Screen Filtering / Sorting | VIN Mgmt screen | Filter/sort for source warehouse
Q | ?? Require more information | UAT14 | Screen Filtering / Sorting | VIN Mgmt screen | Filter/sort for Model Holds
Q | ?? Require more information | UAT15 | Screen Filtering / Sorting | VIN Mgmt screen | Sorting primary & secondary keys, order by functionality
Q | ?? Require more information. Is this the Source Warehouse ID/Origin? | UAT16 | Screen Filtering / Sorting | VIN Mgmt screen | Separate status codes for dealer returns & body shop |  | Comes in as an in transit record. Make it more identifiable.
Q | ?? Require more information | UAT17 | Screen Filtering / Sorting | VIN Mgmt screen | Plant source identifier sorting (KA, KC, KY) |  | Source type sorting capability
Q | ?? Require more information | UAT18 | Screen Filtering / Sorting | VIN Mgmt screen | identifier sorting for Production Line (Line 1 or 2, where applicapable)
YES | RTP yard status can be viewed in VIN management search criteria (yard status to RTP) | UAT19 | Screen Filtering / Sorting | VIN Mgmt screen | Return To Plant filter |  | Dealer return or Factory defect.
YES | Can currently view received date. Advise if alternative field should be added to VIN management screen. | UAT20 | Screen Filtering / Sorting | VIN Mgmt screen | Gate- in identifier |  | Ability to identify units that have been received Gate in .
Q | ??Need more information. Dashboard reports are configured. Is this a new one that is required? | UAT21 | Reporting | Dashboard Reports | Loader ID - be able to filter/sort |  | Want to be able to query how many have been loaded by Employee
Q | ?? Require more information. Can set up a common query within VIN mgmt that can be used. Supply search criteria. | UAT22 | Operational | VIN Mgmt screen | Order by manual Vin assignment |  | Manual assignments from FTZ
NO | Not available. You can run a query and extract to CSV and then email manually. | UAT23 | Operational | Various screens | Export fax/email – auto email and then forward to Fax via email
YES | Search in VIN management on criteria, bulk select, right click and then add hold | UAT24 | Operational | VIN Mgmt screen | Large hold list - dropping in (like BDM
Q | ?? Require more information | UAT25 | Screen Filtering / Sorting | VIN Mgmt screen | Mass maintenance capability
Q | ?? Require more information | UAT26 | Screen Filtering / Sorting | VIN Mgmt screen | Returning cars - (large RTP with description (codes 9 & 10)
YES | VIN management screen search by location | UAT27 | Operational | Yard Mgmt view | Sorting/filter by parking (R, F, T
YES | Parking preferences rules. Super User access Role only. Limited personnel. | UAT28 | Operational | Yard Mgmt view | Setting rules for row ranges to be named for storage by Carrier
NO | .NET responsible for printing. .NET will compile the invoice. N/A for Marysville. | UAT29 | Operational | VIN Mgmt screen | Printing Canada invoices after shipping
YES | Can currently view received date. Advise if alternative field should be added to VIN management screen. | UAT30 | Screen Filtering / Sorting | VIN Mgmt screen | Run a query to show all received units within a time frame
including all status's (received, shipped &/or returned)
YES | ProAct need to complete this effort | UAT31 | Screen Filtering / Sorting | VIN Mgmt screen | Dwell - rule for vins received after a certain time stamp,
dwell clock should not start until next day.
DUPLICATE | Duplicate - see UAT28 | UAT32 | Operational | Yard Mgmt view | Setting rules for row ranges to be named for storage (C for Cassens, tec.)
|  |  | Operational | VIN Mgmt screen | Switching printers in line-off – Line 1 or 2 identifiable |  | Need for Alabama, CH
UAT33
DUPLICATE | Duplicate - see UAT23 | UAT33 | Operational | VIN Mgmt screen | Managing emails/faxes |  | Ability to send emails to Rail companies, Export units
YES | Location configuration, inside Enter and Modify yards. Change Occupancy Status to Free or Unavailable. | UAT34 | Operational | Yard Mgmt view | Inactivating and activating rows and spaces
YES | Parking preferences rules. Super User access Role only. Limited personnel. | UAT35 | Operational | Yard Mgmt view | Parking pointer updating – where unit will go in FTZ |  | Setting up parking preferences
Q | ?? Require more information | UAT36 | Operational | VIN Mgmt screen | Pre-receiving holds
YES | Parking preferences rules. Super User access Role only. Limited personnel. | UAT37 | Operational | Yard Mgmt view | Parking group rules
Q | ?? Require more information. What is stock transfer? | UAT38 | Operational | VIN Mgmt screen | Unassigned vins to stock transfer, and then stock transfer submission
PARTIAL | QIP survey written. No points reward management in place at this stage. Person who did the QIP is captured in the survey and survey can then be extracted. Phase 2 points management (later date). | UAT39 | Operational | VIN Mgmt screen | QIP entries and documentation
YES | Enter and Amend Yard Audits. Set up an Audit. | UAT40 | Operational | VIN Mgmt screen | Physical inventory reconciliation process
Q | ?? Require more information | UAT41 | Operational | VIN Mgmt screen | Stop release on cars getting STOP on rail
YES | Define Rail Manifest for Railcar | UAT42 | Operational | VIN Mgmt screen | Rail row assignment to railheads (rail shipment planning screen in rail option)
NO | linked to UAT7 not available | UAT43 | Operational | VIN Mgmt screen | Be able to remove Zone hold from vins (Utility menu) –
TBD | ???waiting for this to be defined | UAT44 | Operational | VIN Mgmt screen | Body shop transfer process
YES | Honda VIN management | UAT45 | Operational | VIN Mgmt screen | Changing carrier codes and destinations.
YES | Honda VIN management screen. | UAT46 | Operational | VIN Mgmt screen | Document re-prints – monroney and parking tix, export case marks.
Reprint Parking Ticket or Reprint Window Label with list of printers drop down to select from.
TBD | ???waiting for this to be defined | UAT47 | Operational | VIN Mgmt screen | Shuttling units – ELP to MAP transfer
Q | Functionality exists but can you define the expected result? | UAT48 | Operational | VIN Mgmt screen | Truck load entry & ship confirmation
Q | Functionality exists but can you define the expected result? | UAT49 | Operational | VIN Mgmt screen | Rail load entry & ship confirmation

## Defect log
Module | Observations | Valid | Invalid | Retest Passed | Fixed | Open | ETA | Retest Status
Master File Load
Receive&Assignment
Parking Move
UnAssignment
ReturnToPlant
HoldCodes
Pre-Receiving hold
Truck_Shipping
Monroney_Label
Parking Ticket
Warehouse Transfer
BS transfer
Shuttle move
Total | 0 | 0 | 0 | 0 | 0 | 0