## Build Specific
Id# | Code module | Test | Test data | Expected Result | Explanation | Dev Test Results | Explanation | Time required (minutes) | Schedule | Owner | Actual Results
[11 empty] | On PROD deployment | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24
1 | Weld Schedule | Verify that weld schedule screen updates every 30 seconds. | Open the Weld Schedule screen | screen will refresh every 30 seconds | Results as expected | 1 | Not Tested yet. | 1min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
2 | Inventory | Verify that the inventory screen excludes part totals of any carriers in the KD area. | Open the inventory screen | shows proper results | Results as expected | 1 | Not Tested yet. | 1 min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
3 | Carrier Mgt | Verify that carrier search criteria is held while making multiple carrier updates. | Modify several carriers in succession using the carrier update screen. | carrier search criteria will be saved on the screen | Results as expected | 1 | Not Tested yet. | 5 min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
4 | Store-In | Verify that backorder store-in rule only fires once when storing in a backordered part. | place a part on backorder and store in parts using that part | verify that the first carrier selects an empty row and the following carriers enter that same row | Results as expected | 1 | Not Tested yet. | N/A | will need to test in production | Team | 0
5 | Auto Fulfillment | Verify that old production run parts on hold do not prevent selection of newer lots in fulfillment. | place old parts on hold with newer parts | newer parts will be selected in an order | Results as expected | 1 | Not Tested yet. | N/A | will need to test in production | Team
6 | Group Hold | Verify that Group Hold is available to operators | Open the Group Hold screen as an operator user type. | allows user to use the Group Hold feature | Results as expected | 1 | Not Tested yet. | 1 min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
7 | Various | Verify that drop-down menus display properly on WYSE terminals. | Open the application on a WYSE terminal. | all drop-down menus will display properly | Results as expected | 1 | Not Tested yet. | 5 min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 1
8 | Carrier Mgt | Verify that carrier update updates current location and destination. | modify a carrier using the carrier update screen. | carrier information will be updated as expected. | Results as expected | 1 | Not Tested yet. | 1min | 4:40 - 4:45 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
[5 empty] | Totals passed | 8 | Totals Passed |  |  |  | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
d

## OHCV Generic
Id# | Code module | Test | Test data | Expected Result | Notes | Screen used to perform | Time required (minutes) | Schedule | Owner | Actual Results
[10 empty] | 1 =pass 0=fail | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23
1 | Detailed inventroy Report | Run the detailed inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | To keep screenshot of the inventory before the build. | BO report screen at naebo | 5 | 3:45 - 3:50 | Adam Kendell / Steve Kieffer / Bill Klingler | 1
2 | Inventory Report | Run the inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | To keep screenshot of inventory before the build. | BO report screen at naebo | 5 | 3:45 - 3:50 | Adam Kendell / Steve Kieffer / Bill Klingler | 1
3 | Manual move | Move one carrier and test reprocess | Change the destination of the empty carrier at 20-3 to 5-13 and re-process. | Carrier moves to 5-13 |  | Carriers Management | 1 | 4:15 | Adam Kendell | 1 | bar: 2011-11-15 to 2011-11-23
4 | Store In | Test store in manager at ST5-13. | Turn on B100 in the PLC and start sending empties to 5-13 | At ST-13, the carrier will get stored into an available row based upon rules | This starts us turning empties which is required for all of the empty manager tests. | Empty Rules Manager (no screen) | 10 | 4:15 | Bill Klingler | 1 | bar: 2011-11-15 to 2011-11-23
5 | Manual empty | Run manual empty to move empties into old weld line 1 (ST52.) | Find an an area in storage that has an empty row and run Manual Empty on that area. | Carriers move into the old weld line 1 (ST52) |  | Manual Empty | 30 | 4:20 - 4:40 | Adam Kendell / Steve Kieffer / Bill Klingler | 0 | bar: 2011-11-15 to 2011-11-23
6 | Rework screen | Put parts on an empty carrier at the rework stop using the rework screen. | Select the carrier at or move an empty carrier to ST4-5 | Carrier stored in and given a destination | Once complete, be sure to mark the carrier as empty and re-route to an appropriate row. | Rework | 5 | 4:20 - 4:40 | Adam Kendell / Steve Kieffer / Bill Klingler | 0 | bar: 2011-11-15 to 2011-11-23
7 | Manual Order | Place a manual order. | Order 6 carriers to either weld line if any are available. Otherwise, order empty carriers to ST52. | the order will process and send the carriers to the correct weld location or empty storage location. |  | Manual Order | 30 | 4:20 - 4:40 | Adam Kendell / Steve Kieffer / Bill Klingler | 0 | bar: 2011-11-15 to 2011-11-23
8 | Release Manager / Auto fulfillement | Verify that release manager will cause an order to recover if a row inventory is incorrect in storage state. | Place an automatic order for parts in a known incorrect row. | the release manager will detect an incorrect carrier and force a re-select for the active order. | Use resequence screen to change the order of carriers, and use it to correct it after the test. | Ordering | 30 | 5:00 - 5:30 | Adam Kendell / Steve Kieffer / Bill Klingler | 0
9 | Empty Manager | Old weld empty storage low watermark | Old weld line 1 has carriers below 50 and a row has empty carriers in the row | Carriers will release and fill old line 1 | will trigger as empties are stored in | Empty Manager (no screen) | 1 hour | 5:00- 6:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
10 | Empty Manager | Empty carrier storage low watermark | Empty carrier has carriers below 30 | Carriers will release and fill empty return | will trigger as empties are stored in | Empty Manager (no screen) | 1 hour | 5:00- 6:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
11 | Empty Manager | Old weld empty storage high watermark | Old weld line 1 has carriers above 50 and the row has carriers in the row | Carriers will stop sending empty carriers from old line 1 | will trigger once empties stop storing in | Empty Manager (no screen) | 1 hour | 5:00- 6:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
12 | Empty Manager | Empty carrier storage high watermark | Empty carrier return has carriers passing 127 | Carriers will send carriers to be stored in | will trigger once empties stop storing in | Empty Manager (no screen) | 1 hour | 5:00- 6:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
17 | Order Manager | Delivery check processing | All carriers none have inspection required | Carriers at 13 will have destination updated to appropriate destination | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
18 | Order Manager | Delivery check processing | carriers have inspection required | They will stay at stop 13 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
19 | Order Manager | Remaining quantity will go down | After carriers have passed stop 13 | Remaining quantity will decrease by the amount of parts on the carrier | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
20 | Order Manager | Release cycle manager | order with lefts and rights | The lefts will release first and then the rights will release | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
21 | Order Manager | In process of an order | Space not available in weld line | Does not fulfill order | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
22 | Order Manager | Blocked carriers order | Space not available in a area | Does not fulfill the order | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
23 | Order Manager | Release cycle manager | order has filled remaining quantitiy | does not go into cycle to release more carriers | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
24 | Order Manager | multiple orders | an order finishes new order starts | new order does not start until existing order is completed | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
25 | Order manager | A area carriers | carriers being moved | Carrier has destination of stop 13 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
26 | Order Manager | C high carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
27 | Order Manager | C Low carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
[5 empty] | Totals passed |  |  |  |  | 4 | 20 | 20 | 20 | 20 | 20 | 20 | 20