## Build Specific
Id# | Code module | Test | Test data | Expected Result | Explanation | Dev Test Results | Explanation | Time required (minutes) | Schedule | Owner | Actual Results
[11 empty] | On PROD deployment | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24
1 | Carrier Mgt | Verify that a defect can be added, edited, and deleted from a single carrier. | Add, edit, and delete a defect from a carrier using carrier mgt. | A defect will be added, edited, and deleted. | Results as expected | 1 | Not Tested yet. | 5 | 7:10-7:15 | Bill Klingler | 0 | bar: 2011-11-15 to 2011-11-24
2 | Carrier Mgt | Verify that a maintenance user can issue a carrier update. | Update a carrier using maintenance credentials | Carrier will be updated and reprocessed correctly. | Results as expected | 1 | Not Tested yet. | 5 | 6:00 - 6:05 | TBD | 0
3 | Auto Fulfillment | Verify that in mixed/blocked rows, carriers that are on hold status cannot be selected by fulfillment. | Create a mixed blocked row and attempt an automatic order. | Either no carriers will be available, or it will select a different row to pull carriers from. | Results as expected | 1 | Not Tested yet. | 1 | perform during during the week | Team | 0
4 | Empty Management | Verify that empty management will not grab carriers in route to ST52 and send them to ST20-3. | Send carriers from empty storage to hit low watermark to start releasing carriers from ST52. | Empty management will send carriers will fill ST52 before sending to ST20-3. | Results as expected | 1 | Not Tested yet. | n/a | 6:00 to 7:00 | Bill Klingler | 0
5 | Carrier History | Verify that admin and maintenance users can view the update history for a carrier | Search for the history of any valid carrier number | The history for the carrier will be displayed. | Results as expected | 1 | Not Tested yet. | 5 | 7:15 - 7:20 | Bill Klingler | 0
6 | Audit / Error Log | Verify that admin and maintenance users can search and view the Audit Error logs | Search for logs using all of the available fields. | logs will be returned based on the entered criteria | Results as expected | 1 | Not Tested yet. | 5 | 7:20 - 7:25 | Bill Klingler | 0
7 | App Menus | Verify that all drop-down menus function correctly | Open each menu item | Each link will take you to its intended destination. | Results as expected | 1 | Not Tested yet. | 5 | 7:25 - 7:30 | Bill Klingler | 1
[5 empty] | Totals passed | 7 | Totals Passed |  |  |  | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## OHCV Generic
Id# | Code module | Test | Test data | Expected Result | Notes | Screen used to perform | Time required (minutes) | Schedule | Owner | Actual Results
[10 empty] | 1 =pass 0=fail | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23
1 | Detailed inventroy Report | Run the detailed inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | To keep screenshot of the inventory before the build. | BO report screen at naebo | 5 | 5:15 - 5:20 | Kevin Nichols / Adam Kendell | 1
2 | Inventory Report | Run the inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | To keep screenshot of inventory before the build. | BO report screen at naebo | 5 | 5:20 - 5:25 | Kevin Nichols / Adam Kendell | 1
3 | Manual move | Move one carrier and test reprocess | Change the destination of the empty carrier at 20-3 to 5-13 and re-process. | Carrier moves to 5-13 |  | Carriers Management | 1 | 5:45 | Adam Kendell | 0 | bar: 2011-11-15 to 2011-11-23
4 | Store In | Test store in manager at ST5-13. | Turn on B100 in the PLC and start sending empties to 5-13 | At ST-13, the carrier will get stored into an available row based upon rules | This starts us turning empties which is required for all of the empty manager tests. | Empty Rules Manager (no screen) | 10 | 6:00 | Bill Klingler | 0 | bar: 2011-11-15 to 2011-11-23
5 | Manual empty | Run manual empty to move empties into old weld line 1 (ST52.) | Find an an area in storage that has an empty row and run Manual Empty on that area. | Carriers move into the old weld line 1 (ST52) |  | Manual Empty | 30 | 6:15 - 6:30 | Adam or Bill | 0 | bar: 2011-11-15 to 2011-11-23
6 | Rework screen | Put parts on an empty carrier at the rework stop using the rework screen. | Select the carrier at or move an empty carrier to ST4-5 | Carrier stored in and given a destination | Once complete, be sure to mark the carrier as empty and re-route to an appropriate row. | Rework | 5 | 6:15 - 6:30 | Adam or Bill | 1 | bar: 2011-11-15 to 2011-11-23
7 | Manual Order | Place a manual order. | Order 6 carriers to either weld line if any are available. Otherwise, order empty carriers to ST52. | the order will process and send the carriers to the correct weld location or empty storage location. |  | Manual Order | 30 | 6:30 - 7:00 | Adam or Bill | 0 | bar: 2011-11-15 to 2011-11-23
8 | Empty Manager | Old weld empty storage low watermark | Old weld line 1 has carriers below 50 and a row has empty carriers in the row | Carriers will release and fill old line 1 | will trigger as empties are stored in | Empty Manager (no screen) | 1 hour | 6:00- 7:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
9 | Empty Manager | Empty carrier storage low watermark | Empty carrier has carriers below 30 | Carriers will release and fill empty return | will trigger as empties are stored in | Empty Manager (no screen) | 1 hour | 6:00- 7:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
10 | Empty Manager | Old weld empty storage high watermark | Old weld line 1 has carriers above 50 and the row has carriers in the row | Carriers will stop sending empty carriers from old line 1 | will trigger once empties stop storing in | Empty Manager (no screen) | 1 hour | 7:00 - 8:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
11 | Empty Manager | Empty carrier storage high watermark | Empty carrier return has carriers passing 127 | Carriers will send carriers to be stored in | will trigger once empties stop storing in | Empty Manager (no screen) | 1 hour | 7:00 - 8:00 | N/A (ends when B100 is off) | 0 | bar: 2011-11-15 to 2011-11-23
17 | Order Manager | Delivery check processing | All carriers none have inspection required | Carriers at 13 will have destination updated to appropriate destination | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
18 | Order Manager | Delivery check processing | carriers have inspection required | They will stay at stop 13 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
19 | Order Manager | Remaining quantity will go down | After carriers have passed stop 13 | Remaining quantity will decrease by the amount of parts on the carrier | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
20 | Order Manager | Release cycle manager | order with lefts and rights | The lefts will release first and then the rights will release | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
21 | Order Manager | In process of an order | Space not available in weld line | Does not fulfill order | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
22 | Order Manager | Blocked carriers order | Space not available in a area | Does not fulfill the order | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
23 | Order Manager | Release cycle manager | order has filled remaining quantitiy | does not go into cycle to release more carriers | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
24 | Order Manager | multiple orders | an order finishes new order starts | new order does not start until existing order is completed | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
25 | Order manager | A area carriers | carriers being moved | Carrier has destination of stop 13 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
26 | Order Manager | C high carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
27 | Order Manager | C Low carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  |  |  | -1 | bar: 2011-11-15 to 2011-11-23
[5 empty] | Totals passed |  |  |  |  | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 20