## PM
# | PM | Ranking
1 | Pre-Project planning.
2 | Goals not defined-path for project completion not laid out in beginning.
3 | No time to develop technical specs once we get off schedule.
4 | Unrealistic schedule from beginning.
5 | Multiple phases of project happening sametime w/different Project groups.
6 | Prioritizing tasks /PM Scheduling.
7 | Lack of "One Team" approach.
8 | Missed milestones without recourse.
9 | Security method prevented for local PC
10 | Project Management (1) Mulitple project Managers -started with plan for "Flex" programming style for project - Moved to "waterfall" method.
11 | Project Management approach -Rick (good cop) then Kevin (bad cop)
12 | Lack of over all project management, one person over everything.
13 | No catchup plan developed only push schedule out.
14 | Lack of communication for weekend activities.
15 | Project was estimated expecting quicker development using Adjile methodology. This was not well understood or supported.
16 | Planning-not done well & tracking meeting qoals focus.
17 | Concerns not properly escalated to appropriate level of management.
18 | Lack of PM control on technics and tools utilized by the DEV staff
19 | focused direction and re-focusing with Rick early on in Project did not happen -short term goals not met & continued to compound.
20 | Late decision to replace wonderware.

## Project Requirement
# | Project Requirement | Ranking
1 | Requirements either not throughly documented or understood.
2 | Stamping requirements not well defined early.
3 | Scope creap new requirements.
4 | Requirements gathering.
5 | Confusion between simulation & actual situation.
6 | Clarity in Requirements.
7 | Scope of work changes.
8 | Inconsistant direction from customers.

## POC New Tech
POC New Tech
Brand new technology (mes) for MAP/IS.
New Hardware/software.
Communication PLC/MES/APP Network issues.
Not familiar with MES module programming -nuaces /requirements etc…
Not a clear understanding of the hardware capabilities of the MES (not adequate for our entire application)
MES Module not tested thoroughly/unproven.
Hardware capability -No cofirmation of capabilities (QPL)-(MES).
APP /MES/PLC-who assigned dividing lines /capabilities.

## Lack of understanding of existi
Lack of understanding of existing Environment
Idea to keep original PLC Logic not a good choice.
Original PLC Code lacking CP0
PLC upgrades at the same time hindered project.
Assumed no changes required to PLC Logic.
No IS understanding of the existing PLC environment.
PLC Infrastructure not complete before enterprise software.
Grey areas between PLC intregration and ISG.

## testing
Testing
Unable to test prior to implemening changes.
No Test Environment.
Imcomplete simulation.
Time for testing under- estimated.
Testing procedures guidelines not developed prior to coding.
No physical system to test in "train set"
Simulation lacking.
Scenarios not identified ahead for testing.
Testing methods very poor. -Originally planned to "emulate"-failed emulation in timely manner so no apparent method -"great" Test guy introduced to Team hon existant.

## Architectual Solution
Architectual Solution
Lack of Time architectual leadership for the project.
Architechture support MIA (Still not functioning)
Approach the problem. Not clear or inadequate.
Less than perfect Dev. Environment?
Environments (Prod / QA) & Access to them.
AIX Environment Poorly Architechted, Server hardware not provisioned in a timely manner.
Non-Committed agreement b/t development team and corp. on solution approach.

## Technical Resource capability
Technical Resource capability
Lack of technical expertise for development solution.
Possible wrong solution tool selected (Java)
Technical Resource Limitations
Technical challenges with Websphere security
Unable to quickly indentify true root cause of problems.
Lack of Infrustructional expertise.
IT Network design not complete in design phase.
Not clear understanding of Network activity (what/why slowdown) other groups in ISG
Software developed without tech spec.

## Initial Planning
Initial Planning
No true initial standing on the scope of the project.
Original estimate not accurate.
Development time underestimated.
Didn’t understand job scope deep enough.
Adequate time was not allocated to prove out system design.

## Inadequate personel
Initial Planning
Personal changes (key team members)
Project personnel changes.
Losing people in between.
Delay in getting resource help, once concerns were identified.
Resource management
Project Leader not continuous-Gaps in Leader's -Associate turnover.
Hours greatly under-estimated. -Not enough resources to start. Lost resources & did not replace, did not react when lost.
Under-estimate resource needs.
Under-estimated size of effort.
Department project leads with other projects.
Other work with IS interfering.

## Accountability
Accountability
Lacking ownership & accountability to Production floor.