## Sheet1
Report Title | Notes | Ok to Deploy?
Alarm History | Stamping no longer needs this report. Do not deploy. | NO
Area Inventory | Does not appear to use the database key table to define areas. Weld areas are notably absent. | Conditional
Defect Trace Current | Report shows die number instead of die name. Otherwise the report is OK. | Conditional
Defect Trace History | OK | OK
Detailed Inventory | Did not use any filter. All Data looks good. | OK
Inventory Overview | OK | OK
Production Run Inventory | Loaded Qty not showing up in QA. May be an issue with the way the simulation loads and unloads parts on carriers. | OK
Stop Station Efficiency | Stamping no longer needs this report. Do not deploy. | NO
Store Out | If the optional order number is entered, the date criteria does not need to be required. Otherwise, this report is OK. | OK
Weld Deracking Robot History | OK | OK
Weld Orders History | This report still does not run in a reasonable amount of time. Also does not return data. This still may be a QA data problem. | NO