## Remaining Hrs Pivot
Row Labels | Sum of Remaining Work | Resource | Remaining Work
ActivPlant | 8 | EIM Team | 329
Adam | 7 | Emulation | 304
Adam | 16 | Adam | 131
Adam/DBA | 20 | Ambica | 131
Ambica | 131 | Sabo | 69
EIM Team | 329 | Team | 32
Emulation | 304 | Nichols | 20
Kevin | 8 | ActivPlant | 8
Nichols | 12 |  | 1024
Sabo | 69
Team | 32
Team/Adam | 88
Grand Total | 1024

## SAP
Task Name 7/10/12 | Notes | Category | Break Fix or Enhancement | % Complete | Testing Needed | Work | Actual Work | Remaining Work | Duration | Start | Finish | Resource | March 28 | April 4 | April 11 | April 18 | April 25 | May 2 | May 9 | May 16 | May 23 | May 30 | June 6 | June 13 | June 20 | June 27
Totals |  |  |  | 90.37% |  | 841 | 760 | 81
Reliability |  |  |  | 50% |  | 40 | 20 | 20 | 174.34 days? | 2011-12-01 08:00 | 2012-08-01 10:42
Database has a slowdown in the middle of the night (during LET backup for 45 minutes) | Monitoring. No changes left, but it takes time to ensure the problem is still not active | Reliability | Break Fix | 50% |  | 40 | 20 | 20 | 27.78 days | 2012-01-09 08:00 | 2012-03-07 16:07 | Adam/DBA
Clearly document failover process and SLAs. | Requested to test repalcement process for IE3000. | Reliability | Break Fix | 95% |  | 16 | 7 | 9 | 5 days | 2012-04-12 08:00 | 2012-04-18 17:00 | Stamping
WYSE terminal setup not as originally planned.Currently they have been run directo to the IE3000, however they should be home-run to the 4507 on corporate network. | Trying to lock down WYSE terminals. Swap the Stop 13 with one of the Weld 2 pc. Mouse speed - can it be slowed down | Reliability | Break Fix | 100% |  | 48 | 40 | 8 | 11.43 days | 2012-02-02 | 2012-03-01 | Sabo
Detailed Inventory Report for Weld line 2 does not show all carriers | Received statement of work last night. Will sign and get the reporting resource Monday changes to go to Prod 4/21/12 | Reliability | Break Fix | 100% |  | 8 | 0 | 8 | 1 day | 2012-03-09 08:00 | 2012-03-11 | EIM Team
Position in detailed inventory report Position is wrong | Received statement of work last night. Will sign and get the reporting resource Monday changes to go to Prod 4/21/12 | Reliability | Break Fix | 100% |  | 8 | 0 | 8 | 1 day | 2012-04-09 08:00 | 2012-04-09 17:00 | EIM Team
Simulation/ Needs Testing | [8 empty] | 121.17 days | 2012-01-02 08:00 | 2012-06-19 09:22
Redesign Resequence screen | changed 2/22. Block row and then resequence Need to comfirm this is complete. Bill to test | Reliability | Break Fix | 100% | YES | 48 | 40 | 0 | 73.33 days | 2012-01-02 08:00 | 2012-05-02 09:47 | Ambica
Carrier space available for store-in as soon as carrier assigned another destination. We then store-in before the carriers leave and cause a backup at that row. Need to change to make space available only after the carrier leaves a row. | Waiting on simulation | Reliability | Break Fix | 100% |  | 40 | 0 | 40 | 5.36 days | 2012-04-09 08:00 | 2012-05-08 16:51 | Emulation
Check simulation for decision point at stop 49 | Confirmed with Janson and Prod. And simulator do match | Empty carrier management | Break Fix | 100% | YES | 8 | 0 | 0 | 1.38 days | 2012-04-23 08:00 | 2012-05-18 13:51 | Jason
Stop 47 is not filling old weld line 1 | Change has been made but simulation does not match Complete. Need to match simuation to Prod | Empty Carrier Management | Break Fix | 100% | YES | 100 | 0 | 100 | 11.36 days | 2012-08-13 08:00 | 2012-10-16 09:22 | Emulation
Get simulation to take input from multiple source | Actual tasks to get simulation working. Jason is on vacation currently Working now | Reliability | Break Fix | 100% |  | 96 | 76 | 20 | 12 days | 2012-02-02 08:00 | 2012-02-27 17:00 | Emulation
Send input from application | Actual tasks to get simulation working. Jason is on vacation currently Working now | Reliability | Break Fix | 100% |  | 80 | 64 | 16 | 10 days | 2012-02-16 08:00 | 2012-03-25 | Emulation
Test simulation to ensure it works as designed with sending data to it (only fulfillment not Store out) | Adam needs to get the power to execute simulation | Reliability | Break Fix | 90% |  | 80 | 72 | 8 | 10 days | 2012-02-28 08:00 | 2012-03-12 17:00 | Jason
Firewall is wide open. | Frank has stated March 31st at the latest for completion Complete 2/19/2012 | Security | break fix | 100% |  | 83 | 70 | 13 | 24.76 days | 2012-02-02 | 2012-03-12 09:09 | Sabo
(Proj) Document communication needed across the firewall, device by device by 11/28/2011 | Need to add the Static IP address of the call out pc. Will then need to poke hole in the firewall | Security | break fix | 96% |  | 75 | 72 | 3 | 24.76 days | 2012-02-02 | 2012-03-26 15:06 | Sabo
Plan: SMR needed; Mark to make changes documented on the BluePrint. Any to Any rule will be left on and counters set to zero. Each subsequent Sunday following implementation we'll need to remove the any to any rule if there has been a counter increas | Frank has stated March 31st at the latest for completion | Security | Break Fix | 100% |  | 150 | 134 | 16 | 22.38 days | 2012-02-02 | 2012-03-05 11:03 | Sabo
The IP's that are added will be resolved during that week and determine if the traffic should have occured. | Frank has stated March 31st at the latest for completion Complete 4/19/2012 | Security | Break Fix | 100% |  | 150 | 134 | 16 | 22.38 days | 2012-02-02 | 2012-03-30 11:03 | Sabo
(Jeffers) Turn on firewall rules by 4/25/12 | Frank has stated March 31st at the latest for completion Complete 4/19/2012 | Security | Break Fix | 100% |  | 48 | 40 | 8 | 7 days | 2012-03-13 | 2012-04-03 11:03 | Sabo
NEED FOR DEVELOPER SUPPORT. MUST HAVE ACCESS. MES AND PLC.Need team discussion to understand requirements | PC installed at BB17 MES. Need to confirm working | Security | Break Fix | 95% |  | 24 | 23 | 1 | 1.2 days | 2012-08-10 16:19 | 2012-08-14 08:55 | Stamping
Empty Carrier management |  |  |  | 50% |  | 80 | 40 | 40 | 53.9 days | 2012-02-08 | 2012-04-23 16:11
Change rules for empty carrier manager after simulation verification | Waiting on simulation for verification but it is believed that the way empty carrier manager is good the way it is in production Need to complete verification | Empty carrier management | Break Fix | 100% | YES | 80 | 40 | 0 | 6.58 days | 2012-05-07 08:00 | 2012-05-25 16:11 | Emulation
Want mixed rows with empties in the front uncovered | Complete 4-14-2012 | Empty carrier management | Break Fix | 100% |  | 10 | 0 | 10 |  |  |  | Adam
More robust alarm functionality. | Signoff has been completed developer can begin Complete 4-14-2012 | Alarm | Phase 2 | 100% |  | 16 | 9 | 7 | 2 days | 2012-05-01 08:00 | 2012-05-02 17:00 | Ambica
Infrastructure setup | Signoff has been completed developer can begin In-progress 4-19-2012 | Alarm | Phase 2 | 100% |  | 40 | 0 | 40 | 10 days | 2012-04-18 08:00 | 2012-05-02 | Ambica
Paging added | Signoff has been completed developer can begin In-progress 4-19-2012 | Alarm | Phase 2 | 100% |  | 20 | 0 | 20 | 5 days | 2012-05-02 08:00 | 2012-05-09 | Ambica
Email added | Signoff has been completed developer can begin In-progress 4-19-2012 | Alarm | Phase 2 | 100% |  | 20 | 0 | 20 | 5 days | 2012-03-20 08:00 | 2012-03-27 | Ambica
Clear all alarms setup | Signoff has been completed developer can begin Complete 4-14-2012 | Alarm | Phase 2 | 100% |  | 20 | 0 | 20 | 5 days | 2012-03-27 08:00 | 2012-04-03 | Ambica
Alarm history setup | Signoff has been completed developer can begin Complete 4-14-2012 | Alarm | Phase 2 | 100% |  | 8 | 0 | 8 | 1 day | 2012-03-09 08:00 | 2012-03-12 | Ambica
Monitoring and Notification in the event of failure needs to be explicitly documented (OHCV web app, DB). Escalation procedure in case MES cannot communicate with app is not setup. | On-hold because of bug fixes. | Alarm | Phase 2 | 0% |  | 0 | 0 | 0 | 1 day | 2012-03-15 08:00 | 2012-03-15 17:00 | Stamping
(Proj)1. Provide a list of log files and text to monitor, and Notes group for each. (Mfg IT) | Signoff has been completed developer can begin Net IQ. Looking to complete within the application. This item has been replaced by alarming and alerting portion of the app. | Alarm | Phase 2 | 0% |  | 8 | 0 | 8 | 1 day | 2012-05-09 08:00 | 2012-05-10 | Ambica
Fulfillment | [8 empty] | 61.31 days | 2012-03-26 | 2012-06-19 10:28
Fulfillment ordering | (Re-ordering Situation) Row out-of-seq will break order. Trying to test in simuation but difficult to do that way. Not duplicated in simulation yet. | Fulfillment | Break Fix | 94.81% |  | 135 | 128 | 7 | 8.57 days | 2012-04-08 | 2012-06-19 10:28 | Adam
Additional Reporting | Fixed reports not moved. Have not heard from Danny | Reporting | Phase 2 | 97.5% |  | 320 | 312 | 8 | 40 days | 2012-02-13 08:00 | 2012-04-09 | EIM Team
Prompted ordering (look at weld on schedule and suggest weld orders for the shift) | Bill to follow up with Weld. WE dealing with NM | User Experience | Phase 2 | 66.67% |  | 24 | 16 | 8 | 5 days | 2012-09-10 08:00 | 2012-09-18 13:48 | Team/Adam
Press Activity Manager (press scheduling tool) Of current shows die number, model name, current production run number, and location carriers are stored for each press | Screen is complete, need to verify with Customer. | User Experience | Phase 2 | 100% |  | 8 | 8 | 0 | 1 day | 2012-06-11 08:00 | 2012-06-11 17:00 | Team/Adam
Enhanced inventory where enter model shows parts per carrier and shows when space will be available to help predict scheduling (Possible enhancement needed) | Removed per customer | User Experience | Phase 2 | 25% |  | 40 | 0 | 40 | 5 days | 2012-06-29 08:00 | 2012-07-20 10:49 | Team/Adam
Signboards (solved by activeplant) | Joe is working with Rocky Kellys active plant to fulfill this requirement. It would pull the data out of the system and display the information. Complete | User Experience | Phase 2 | 100% |  | 8 | 0 | 8 | 1.76 days | 2012-04-10 11:30 | 2012-06-01 09:31 | ActivPlant
Break Fix |  |  |  | 19% |  | 16 | 13 | 3 | 114.3 days? | 2011-12-08 08:00 | 2012-05-16 10:24
Tags still have hex instead of decimal causing multiple reporting issue | This is going in on March 24th | User Experience | Break Fix | 0% |  | 120 | 0 |  | 15 days | 2012-03-29 13:00 | 2012-05-16 10:24
When blocking rows if too many rows are blocked it will cause error conditions | Fix Should be in next build on the 22nd Complete | Fulfillment | Break Fix | 100% |  | 16 | 13 | 3 | 2 days? | 2011-12-12 08:00 | 2011-12-13 17:00 | Adam
In Die or model config screen unable to delete die or model | Coding done; testing in progress, will need to schedule implementation. Will be part of June 21st build. | User Experience | Break Fix | 90% |  | 4 | 0 | 1 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00 | Adam
M1000 trigger status timing | Timing change; Issue to be reviewed in Thursday trace meetings. Stamping working with Phantom to resolve. Does not appear to be an issue with M1000 | Reliability | Break Fix | 100% |  | 40 | 0 | 0 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00 | Stamping
M9000 trigger taking hard code of status out | Complete | Reliability | Break Fix | 100% |  | 0 | 0 | 0 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00
Row resequence Bug | Need to confirm issue still exists | Reliability | Break Fix | 0% |  | 0 | 0 | 0 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00
Release manager auto correct issue | PROD OK; Outstanding changes | Reliability | Break Fix | 75% |  | 46 | 40 | 6 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00 | Adam\Ambica
When carrier is inspection required it will need to be stopped at stop 13 | Need Adam and Bill to test | Reliability | Break Fix | 90% |  | 5 | 4 | 1 | 1 day? | 2011-12-01 08:00 | 2011-12-01 17:00 | Bill\Adam
Item added 4 20
Defect type to defect screen. Also a note field | Going in the 5/17 build | User Experience | Break Fix
Document Trigger process | Adam and Bill to work through | User Experience | Documentation | 50% |  | 12 | 6 | 6 |  |  |  | Adam\Bill
Failed Ping situation | Trying to trace the origin on issue. | Reliability | Break Fix | 50% |  | 100 | 80 | 20 |  |  |  | Adam