## Sheet1
Id# | Code module | Test | Test data | Expected Result | Explanation | Dev Test Results |  | Actual Results
[6 empty] | 2011-12-14 |  | 2011-12-17 | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24
1 | M1000 | Trigger fires when a carrier reaches a stop. | A carrier is selected to move through the system. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | M9000 | Trigger fires when a carrier reaches load in point. | A carrier is loaded at the loading station. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | M9000 | Trigger fires when entering a row. | A carrier enters a row. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Empty Return | Trigger fires when empty reaches ST20-3 | Empty carrier reaches ST20-3. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Application Carrier Update | Application can update all fields of a carrier movement. | Manually update a carrier through the application. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
6 | Application Carrier Update | Manual Order out correctly updates and releases carriers from a row. | Place a manual order through the application. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
7 | Application Carrier Update | Manual Emptly release correctly updates and releases carriers from a row. | Place a manual empty release through the application. | MES and DB2 database records will be updated for that carrier and a log entry will be generated. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
8 | Reports | Area inventory report. | Run report | Report will pull data from the new DB2 database. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
9 | Reports | Detailed inventory report | Run report | Report will pull data from the new DB2 database. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
10 | Reports | Inventory Overview | Run report | Report will pull data from the new DB2 database. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
11 | Reports | Store Out | Run report | Report will pull data from the new DB2 database. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
12 | Reports | Weld Deracking Robot History | Run report | Report will pull data from the new DB2 database. | Results as expected | 1 | Will test on 12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
[5 empty] | Totals passed | 12 | Totals Passed | 0 | 4 | 4 | 4 | 4 | 4 | 12 | 12 | 12