## Build Specific
Id# | Code module | Test | Test data | Expected Result | Explanation | Dev Test Results |  | Actual Results
[6 empty] | 2012-01-25 |  | On PROD deployment | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24
1 | Stop Mgt | Change stop name to be longer than 20 chars | update a stop with a name longer than 20 characters | Stop name will change | Results as expected | 1 | Successful | 1 | bar: 2011-11-15 to 2011-11-24
2 | Carrier Mgt | Verify that carrier update will reprocess and show source. | Reprocess an empty carrier at a store in stop. | Carrier will be updated, source will be the logged in user, and the carrier will get a store in destination. | Results as expected | 1 | Successful | 1
3 | Inspection | Verify that Inspection screen bug is corrected. | Update a carrier at an inspection stop using the inspection screen. | Carrier will be updated as specified in the inspection screen. | Results as expected | 1 | Successful | 1
4 | Weld Schedule | Check weld schedule screen. | Verify data matches PLC | Data will match values in the PLC | Results as expected | 1 | Left and right quantities are flipped on line 1 on line 2 no way to tell because they were same number. Was flipped in the MES | 1 | bar: 2011-11-15 to 2011-11-24
5 | Manual Empty | Verify manual empty uses the release manager | perform a manual empty on an empty row. | Carriers will release using the release manager | Results as expected | 1 | Successful | 1 | bar: 2011-11-15 to 2011-11-24
6 | Auto Fulfillment | Verify auto fulfillment uses the release manager | place an automatic order | Carriers will release using the release manager | Results as expected | 1 | Unable to test because both weld lines are full schedule Monday morning | 0 | bar: 2011-11-15 to 2011-11-24
7 | Inventory | Verify title text change | open inventory screen | IN STORAGE ALL ROWS 1-35 | Results as expected | 1 | Successful | 1
8 | Various screens | verify text change from die to model | open screens and verify that model is changed to die: carrier mgt, detailed inventory, all inspection screens, and all inventory screens. | The word "die" will be replaced with "model." | Results as expected | 1 | Successful | 1
9 | Carrier Mgt | Verify that row 35 shows carrier position | perform a search for row 35 in carrier mgt. | the Row Position field will be filled. | Results as expected | 1 | Successful | 1
10 | Rework | Verify that the default Model is blank and that an entry is required | attempt to send a rework carrier with no Model selected | the screen will return an error | Results as expected | 1 | Successful | 1
11 | Rework | Verify that rework screen updates the die, quantity, and destination correctly. | send a rework carrier into storage | the die, quantity, and destination will be correct | Results as expected | 1 | There was an error while trying to save the update in production. This does not hapopen in development | 0
12 | Carrier Mgt | Verify that the correct destination is given at each of the weld delivery points. | send carriers to each weld line. | at each weld delivery point, (ST101 and ST5,) every carrier will receive a destination to the weld robot stops. | Results as expected | 1 | Unable to test because both weld lines are full schedule Monday morning | 0
13 | Row Mgt | Verify that a row can be excluded from automated store in and store out. | Have an empty carrier stored in. Mark the chosen row as out of order and attempt to store in another empty carrier. | Store in will choose a different row to store the empty carrier. | Results as expected | 1 | Successful | 1
14 | Release Manager | Verify that release manager releases from only one row at a time and initiates the next row release. | using Carrier Mgt, send four empty carriers to ST52 from two different rows in the same storage area using the release manager. | The first row told to release will release, and the next row will begin releasing once the first row is complete. | Results as expected | 1 | Successful | 1
[5 empty] | Totals passed | 14 | Totals Passed | 11 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## OHCV Generic
Id# | Code module | Test | Test data | Expected Result | Explanation | Screen used to perform | Time required | Actual Results
[8 empty] | Before | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | 2011-11-22 | 2011-11-23 | After
| Detailed inventroy Report | Run the detailed inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | Only doing this because of how many empties usually just keep screenshot of the rows | BO report screen at naebo | 30 | 1 | [7 empty] | 1
| Inventory Report | Run the inventory report | Run the report and visually check the overhead | Overhead inventory matches the report | Only doing this because of how many empties usually just keep screenshot of the rows | BO report screen at naebo | 30 | 1 | [7 empty] | 1
1 | Manual move | Move one carrier | Pick the carrier at 20-3 | Carrier moves to 5-13 | Successful | Carriers Management | 10 | 1 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
2 | Empty manager | Carrier gets stored into an available row based upon rules | Carrier is at 5-13 and empty | Carrier gets stored in | Successful | Empty Rules Manager (no screen) | 30 | 1 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
3 | Manual empty | Select the empty carrier that was just stored in and it goes into ST52 | Empty carriers are moved to ST52 | Carriers move into the old weld line 1 |  | Manual Empty | 30 | 1 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
4 | Rework screen | Move a Carrier to 4-5 and is able to be stored in | Carrier stored in and given a destination product is obselete product | Carrier moves to correct row |  | Rework | N/A | 0 | [7 empty] | 0 | bar: 2011-11-15 to 2011-11-23
5 | Manual Order | Check manual order | Order 6 carriers if they are available | the order will process and send the carriers to the correct weld location | Unable to be tested Weld 1 and Weld 2 were both full | Manual Order | N/A | 0 | [7 empty] | 0 | bar: 2011-11-15 to 2011-11-23
11 | Empty Manager | Releasing from one row | Empty storage is really low | Only release 6 carriers from 1 row |  | Empty Rules Manager (no screen) | 30 | 1 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
12 | Empty watermark | Old weld empty storage watermark | Old weld line 1 has carriers below 50 and a row has empty carriers in the row | Carriers will release and fill old line 1 | The old wel line 1 was filled when it hit its low watermark | Empty Rules Manager (no screen) | 1 hour | 0 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
13 | Empty watermark | Old weld empty storage watermark | Old weld line 1 has carriers above 50 and the row has carriers in the row | Carriers will stop sending empty carriers from old line 1 | The old weld line 1 stopped once it hit its full watermark | Empty Rules Manager (no screen) | 1 hour | 0 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
14 | Empty watermark | Empty Carrier Return empty storage watermark | Empty carrier has carriers below 30 | Carriers will release and fill empty return | Empty Return was filled when it hit its low watermark | Empty Rules Manager (no screen) | 1 hour | 0 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
15 | Empty watermark | Empty Carrier empty storage watermark | Empty carrier return has carriers passing 127 | Carriers will send carriers to be stored in | This is simulated through the PLC by forcing the PLC B100 in CP0 | Empty Rules Manager (no screen) | 1 hour | 1 | [7 empty] | 1 | bar: 2011-11-15 to 2011-11-23
16 | Reprocess | Create a stuck carrier and send reprocess | A carrier is "stuck" at a location | After reprocess is set it will move the carrier | To create a stuck carrier …Did not have to as there was a need to reprocess a carrier | Carriers Management | 5 | 1 | [7 empty] | 1
17 | Order Manager | Delivery check processing | All carriers none have inspection required | Carriers at 13 will have destination updated to appropriate destination | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
18 | Order Manager | Delivery check processing | carriers have inspection required | They will stay at stop 13 | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
19 | Order Manager | Remaining quantity will go down | After carriers have passed stop 13 | Remaining quantity will decrease by the amount of parts on the carrier | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
20 | Order Manager | Release cycle manager | order with lefts and rights | The lefts will release first and then the rights will release | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
21 | Order Manager | In process of an order | Space not available in weld line | Does not fulfill order | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
22 | Order Manager | Blocked carriers order | Space not available in a area | Does not fulfill the order | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
23 | Order Manager | Release cycle manager | order has filled remaining quantitiy | does not go into cycle to release more carriers | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
24 | Order Manager | multiple orders | an order finishes new order starts | new order does not start until existing order is completed | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
25 | Order manager | A area carriers | carriers being moved | Carrier has destination of stop 13 | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
26 | Order Manager | C high carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
27 | Order Manager | C Low carriers | carriers being moved | Carrier has destiantion of stop 13-1 | Not required Yet | Ordering |  | -1 | [7 empty] | -1 | bar: 2011-11-15 to 2011-11-23
[5 empty] | Totals passed |  |  | 8 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 11